## Sheet1
# of Days | Tasks |  |  |  | #6
1 | purchase_lot 2 |  | design_house 5 |  |  | (purchase_lot 2)
2
3 | [5 empty] | (design_house 5)
4
5 |  |  |  |  | 7-1=6 | (get_permit 1 purchase_lot design_house)
6 | get_permit 1 | get_bids 14 | order_windows_doors 3
7 |  |  |  |  | 7-1=6 | (get_bids 14 purchase_lot design_house)
8
9 |  |  | get_windows_doors 10 |  | 7-1+14=20 | (select_subs 2 get_bids)
10
11 |  |  |  |  | 7-1+2+14=22 | (excavate 1 get_permit select_subs)
12
13 |  |  |  |  | 7-1+1+14+2=23 | (construct_basement 7 excavate)
14
15 |  |  |  |  | 7-1=6 | (order_windows_doors 3 purchase_lot design_house)
16
17 |  |  |  |  | 9 | (get_windows_doors 10 order_windows_doors)
18
19 |  |  |  |  | 22 | (frame 12 get_permit select_subs)
20 |  | select_subs 2
21 |  |  |  |  | 34 | (rough_plumbing 5 frame)
22 |  | excavate 1 | frame 12
23 |  | construct_basement 7 |  |  | 34 | (rough_electric 3 frame)
24
25 |  |  |  |  | 34 | (roof 4 frame)
26
27 |  |  |  |  | 39 | (install_windows_doors 7 get_windows_doors rough_plumbing rough_electric)
28
29 |  |  |  |  | 46 | (vapor_barrier_insulation 2 roof install_windows_doors)
30
31 |  |  |  |  | 48 | (drywall 5 vapor_barrier_insulation)
32
33 |  |  |  |  | 53 | (inside_paint 3 drywall)
34 |  | roof 4 | rough_plumbing 5 | rough_electric 3
35 |  |  |  |  | 56 | (cupboards 3 inside_paint)
36
37 |  |  |  |  | 56 | (carpet_floor 5 inside_paint)
38
39 |  |  | install_windows_doors 7 |  | 39 | (lights 2 inside_paint)
40
41 |  |  |  |  | 56 | (plumbing_heating 6 inside_paint)
42
43 |  |  |  |  | 46 | (siding 2 roof install_windows_doors)
44
45 |  |  |  |  | 48 | (outside_paint 3 siding)
46 |  | siding 2 | vapor_barrier_insulation 2
47 |  |  |  |  | 62 | (move_house 1 cupboards carpet_floor lights plumbing_heating outside_paint)
48 |  | outside_paint 3 | drywall 5
49 |  |  |  |  | 63 | (connections 2 construct_basement move_house)
50
51 |  |  |  |  | 63 | (landscape 4 construct_basement move_house)
52
53 |  |  | inside_paint 3 |  | 67 | (move_in 0 landscape connections)))
54
55
56 | plumbing_heating 6 | carpet_floor 5 | cupboards 3 | lights 2
57
58
59
60
61
62 | move_house 1
63 | connections 2 |  | landscape 4
64
65
66
67 | move_in 0